## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-00 | Learn and revise Java basics(OOP,collections,exceptions) | MUST HAVE | NA | Geesala Lavanya | 3- Completed
Sprint 1 | Sprint 1 | US-01 | Create the project setup and run the Spark server | MUST HAVE | US-00 | Geesala Lavanya | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Design account class and repository to handle account balance | MUST HAVE | US_01 | Geesala Lavanya | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Build API to allow users to open new accounts | MUST HAVE | US_02 | Geesala Lavanya | 3- Completed
Sprint 2 | Sprint 2 | US-04 | Implement deposit functionally | MUST HAVE | US-03 | Geesala Lavanya | 3- Completed
Sprint 2 | Sprint 2 | US-05 | Create withdrawal feature with exception handling | MUST HAVE | US-03 | Geesala Lavanya | 3- Completed
Sprint 2 | Sprint 2 | US-06 | Implement fund transfer between two accounts | MUST HAVE | US-04,US-05 | Geesala Lavanya | 3- Completed
Sprint 2 | Sprint 2 | US-07 | Validate transactions and store transaction history | MUST HAVE | US-04,US-05 | Geesala Lavanya | 3- Completed
Sprint 3 | Sprint 3 | US-08 | Create service to check for low account balance | SHOULD HAVE | US-02 | Geesala Lavanya | 3- Completed
Sprint 3 | Sprint 3 | US-09 | Implement low balance alert service | SHOULD HAVE | US-08 | Geesala Lavanya | 3- Completed
Sprint 4 | Sprint 4 | US-10 | Create simple UI for account and transactions | COULD HAVE | NA | Geesala Lavanya | 3- Completed
Sprint 4 | Sprint 4 | US-11 | Connect frontend UI with backend APIs | SHOULD HAVE | US-10 | Geesala Lavanya | 3- Completed
Sprint 4 | Sprint 4 | US-12 | Test all features of the banking application | SHOULD HAVE | US-11 | Geesala Lavanya | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 48 | 7 | 8 | 10 | 7 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | 1 | Java basics revision(OOP,Collections,Exceptions) | 2025-12-01 | 2025-12-02 | Geesala Lavanya | Others | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 2 | Project setup & Github repository initialization | 2025-12-01 | 2025-12-01 | Geesala Lavanya | Others | 3-Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 3 | Spark Java server setuo and configuration | 2025-12-02 | 2025-12-02 | Geesala Lavanya | Others | 3-Completed | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 4 | Design Account model(figures &structure) | 2025-12-03 | 2025-12-03 | Geesala Lavanya | Coding | 3-Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 5 | Implement Account class in Java | 2025-12-04 | 2025-12-05 | Geesala Lavanya | Coding | 3-Completed | 4 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 6 | Create Account Repository using collections | 2025-12-05 | 2025-12-06 | Geesala Lavanya | Coding | 3-Completed | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 7 | Implement Create Account API endpoint | 2025-12-05 | 2025-12-06 | Geesala Lavanya | Coding | 3-Completed | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 8 | Validate account creation input & error handling | 2025-12-05 | 2025-12-06 | Geesala Lavanya | Coding | 3-Completed | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 9 | Design transaction model | 2025-12-08 | 2025-12-09 | Geesala Lavanya | Coding | 3-Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 10 | Implement deposit functionality | 2025-12-09 | 2025-12-10 | Geesala Lavanya | Coding | 3-Completed | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 11 | Implement withdrawal functionality | 2025-12-10 | 2025-12-11 | Geesala Lavanya | Coding | 3-Completed | 4 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 12 | Implement transfer functionality | 2025-12-12 | 2025-12-13 | Geesala Lavanya | Coding | 3-Completed | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 13 | Design alert module | 2025-12-15 | 2025-12-15 | Geesala Lavanya | Coding | 3-Completed | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on overall Banking Simulator project requirements and features | Discussed project scope with mentor and referred to sample project documents
Sprint 1 | Day 4 | Faced difficulty in creating proper project structure configuring Spark server | Reorganized the project folders and successfully configured the Spark server
Sprint 2 | Day 6 | Difficulty in designing account model and repository classes | Reviewed design patterns and improved the account class structure
Sprint 2 | Day 7 | Errors occurred while implementing deposit and withdrawal functionalities | Debugged the code and added necessary validation logic
Sprint 2 | Day 9 | Confusion in managing fund transfer between multiple accounts | Implemented transfer logic with proper account verification and balance checks
Sprint 3 | Day 12 | Issues while implementing low balance alert functionality | Analyzed alert logic and tested threshold conditions
Sprint 4 | Day 16 | Difficulty in connecting frontend with backend APIs | Tested APIs using Postman and corrected request and response mappings
Sprint 4 | Day 18 | Minor issues during end-to-end testing of banking transactions | Executed multiple test cases and fixed identified bugs

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-01 | 2025-12-12 | Geesala Lavanya | Understanding project requirements carefully before coding | Starting work without clear understanding | Practicing Java basics regularly | Discussed doubts with mentor and studied examples
2 | Sprint 2 | 2025-12-15 | 2025-12-19 | Geesala Lavanya | Writing validations before coding logic | Ignoring error cases in code | Following proper code structure | Added validations and fixed logic errors
3 | Sprint 3 | 2025-12-22 | 2026-01-02 | Geesala Lavanya | Testing features while developing | Delaying testing until the end | Checking each feature separately | Fixed issues early by regular testing
4 | Sprint 4 | 2026-01-05 | 2026-01-16 | Geesala Lavanya | Testing APIs before UI integration | Skipping API testing | Using Postman for API testing | Corrected API issues before connecting UI
5 | Sprint 5 | 2026-01-19 | 2026-01-23 | Geesala Lavanya | Doing complete application testing | Rushing final testing | Following step-by-step testing | Fixed bugs and improved application performance
6
7